Sr. No.	Name	Order	Time Needed	Actual Start	Predicted Finished	Actual Finished	Delay by (days)
1	Introduction	Sixth	15 days	11th December	26th December	11th December	+14
2	Theory	Ninth	15 days	28th December	12th January
3	Detector	Seventh	10 days	12th December	22st December	21st December	+1
4	Reconstruction	Eighth	7 days	22nd December	29th December	28th December	+1
5	Measurement	First	25 days	28th October	22nd November	24th November	-2
6	Th. Predictions	Second	10 days	24th November	4th December	4th December	0
7	Alphas	Third	7 days	5th December	12th December	7th December	+5
8	Summary	Fourth	5 days	7th December	12th December	8th December	+4
9	Abstract	Fifth	5 days	8th December	12th December	9th December	+4
10	Hardware	Thirteen	7 days
11	Ackn.	Tenth	5 days
12	Biblio/Pub	Eleventh	5 days
13	Publications	Twelfth	2 days
	Thesis	Full	120 days	28th October	25th February

Sr. No.	Name	Back Side Blank
1.	Title	Yes
2.	Dedication	Yes
3.	Acknowledgement	Yes if odd
4.	Abstract	Odd
5.	Contents	Odd
6.	List of Figures	Odd
7.	List of Tables	Odd
8.	Chapter-1	Odd
9.	Summary	Odd
10.	Bibliography	Odd
11.	CMS Public Notes	-
12.	CMS AN Notes	-
13.	Publication	-